UGANDA CHRISTIAN UNIVERSITY

Directorate of Postgraduate Studies

____________________________________________________________

“A Centre of Excellence in the Heart of Africa”

REGULAR SUPERVISION REPORT

Supervisor’s Name: DAPHNE NYACHAKI BITALO

Student’s Name: REMMY BISIMBEKO Reg. No: J24M19/011

Proposal Concept Approval Date: 	1ST JULY 2025

Return Date from Data Collection: 	1st FEBRUARY 2026

| Session | Material Reviewed |  | Date & Time | Duration of Session | Signatures |  | Progress Rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Student | Supervisor |  |
| 1. | Proposal VIVA feedback |  | 25th June- 14th July 2025 | 2 hour in-person meeting 4 hours document feedback (google drive) |  |  | Student response to Research Proposal received 22 July 2025. |
| 2. | Research Implementation plan |  | 25th July 2025 | 2 hours in-person meeting |  |  | Implementation plan structured. Action plan: Student approved to start data collection and drafting thesis. |
| Research Coordinator’s Name: ………..…………………………………..………………. Signature: ……………….………………… |  |  |  |  |  |  |  |
| 3. | Student-advisor Agreement | 6th August 2025 |  | 2 hours |  |  | Agreement signed incorporated the implementation plan, and expected outputs and timelines reviewed. |
| 4. | Student progress reporting | 24th September 2025 |  | 3 hours conducted via email/google drive |  |  | Feedback given by supervisor. Student didn’t attend this meeting. |
| Research Coordinator’s Name: ………..………………………………………..…………. Signature: ……………….………………… |  |  |  |  |  |  |  |
| 5. | Student progress reporting | 6th November 2025 |  | 3 hours conducted via email/google drive |  |  | Student submits 1st Thesis Draft. Supervisor Feedback given for implementation. |
| 6. | Conference abstract and journal writing exercise | December 2025 |  | 4 hours on Google drive |  |  | Student submitted an abstract and a review article draft by 13th December 2025. However, supervisor feedback was not addressed by student. |
| Research Coordinator’s Name: ………..………………………………………………..…. Signature: ……………….………………… |  |  |  |  |  |  |  |
| 7. | Thesis Review Meeting | 27th and 30th January 2026 |  | 2 hour Online meetings |  |  | Thesis draft 2 reviewed in meeting. Student progress is slow due to work engagements. New deadlines set. |
| 8. | Thesis Methodology review | 22nd March 2026 |  | 2 hours on zoom, several hours on google drive |  |  | 3rd to 5th drafts of the thesis complete till the Methodology section. Student should respond to feedback and send a 5th draft with addition of Results. |
| Research Coordinator’s Name: ………..…………………………………………….……. Signature: ……………….………………… |  |  |  |  |  |  |  |
| 9. | Thesis Results review | 26th March 2026 |  | 2 hours on zoom, several hours on google drive |  |  | 6th draft thesis complete till the Results section. Student should respond to feedback and send a final draft with a discussion. |
| 10. | Final Thesis Review | 1st June and 15th June 2026 |  | 2 hours Google drive |  |  | Student submitted tow final drafts, including supervisor feedback. |
| 11. | Approval of thesis for submission for external examination | 15th June 2026 |  | Email |  |  | Final thesis draft submitted for external examination. VIVA completed. Student approved for graduation in October 2026. |
| 12. | Drafting Journal Article | 16th August todate |  | Google collab/Email |  |  | Draft article title: Spending Efficiency Over Spending Volume: A Machine Learning Framework for Personalised Voice Bundle Recommendation in Emerging Prepaid Markets. Journal: Journal of Business Research |
| 13. | Thesis VIVA Defense and Post-VIVA Corrections | 23rd July – 10th August 2026 |  | 3 hours VIVA defense + several hours corrections via Google Drive / email |  |  | VIVA defense held 23rd July 2026. Examiner and panellist comments received. Student addressed all 22 comments and submitted revised thesis with signed Post-VIVA Compliance Form by 10th August 2026. |
| 14. | Drafting Journal Article | 16th August 2026 to date |  | Google Drive / Email / Github |  |  | Draft article title: 'Spending Efficiency Over Spending Volume: A Machine Learning Framework for Personalised Voice Bundle Recommendation in Emerging Prepaid Markets.' Target journal: Journal of Business Research (JBR, Elsevier). |
| Research Coordinator’s Name: ………..…………………………………………….……. Signature: ……………….………………… |  |  |  |  |  |  |  |

Instructions/Guidelines

Each supervisor will meet with the student at least twice a month for a total of four hours. This tool should be signed by both the supervisor and student each time they meet. The supervisor shall deliver this reporting tool to the School Research Coordinator for signing, every month.

The School Research Coordinator shall write a report to the Dean, School for Research and Postgraduate Studies regarding the student’s progress every month.

Progress Rating (By Supervisor)

1.  Unsatisfactory             2. Satisfactory          3. Good            4. Very good               5. Excellent

Cc Head of Department                                                                                        Cc Co-supervisor (if there is one)